# NATIONAL BUILDERS CORP

# PROJECT PLANNING GUIDE

## "From Idea to Impact"

Complete 20-Page Simple Planning Tool | Ages 7-17 | 2025 Edition

# TABLE OF CONTENTS

1. Introduction: Why Planning Matters

2. Step 1: Understand the Problem

3. Step 2: Design Your Solution

4. Step 3: Create Your Action Plan

5. Step 4: Map Your Resources

6. Step 5: Plan for Impact Measurement

7. Step 6: Build Sustainability

8. Sample Project Examples

9. Common Mistakes to Avoid

10. Final Planning Checklist

# INTRODUCTION: WHY PLANNING MATTERS

## Welcome to Project Planning!

Many people have great ideas but poor execution. Why? Because they skip planning.

The difference between:

A dream and a goal = A written plan

An idea and a project = An action plan

Hope and results = Measurement plan

"Failing to plan is planning to fail."

This workbook will guide you step-by-step to create a solid project plan. Don't rush through it. Take your time. A good plan saves you months of wasted effort.

## HOW TO USE THIS WORKBOOK

1. Read each section carefully

2. Answer every question honestly

3. Discuss your answers with your team/mentor

4. Revise your plan as you learn more

5. Keep this workbook handy - refer to it throughout your project

## WHAT MAKES A GOOD PROJECT PLAN?

A good plan is:

✅ SPECIFIC - Clear details, not vague ideas

✅ REALISTIC - You can actually do it with available resources

✅ MEASURABLE - You can prove your impact with numbers

✅ TIME-BOUND - Has deadlines and milestones

✅ FLEXIBLE - Can adapt when things change

Let's begin planning your nation-building project!

# STEP 1: UNDERSTAND THE PROBLEM

## WHY THIS MATTERS

You can't solve a problem you don't understand. Many projects fail because they address symptoms, not root causes.

Example:

SYMPTOM: Children are failing exams

ROOT CAUSE: They can't read well (poor literacy in early grades)

If you only focus on exam prep, you won't solve the real problem. You must dig deeper.

## 1.1 DESCRIBE THE PROBLEM

What problem are you solving?

Write it in ONE simple sentence:

_______________________________________________

_______________________________________________

Good examples:

"Children in my community don't have clean water to drink"

"Youth in my area have no job skills and are unemployed"

"Our school has no library, so students can't practice reading"

Bad examples (too vague):

"Education is bad" (What exactly is bad about it?)

"The community needs help" (What kind of help?)

"Things are not working" (What things?)

## 1.2 WHERE IS THIS PROBLEM?

Be specific about location.

State: _______________________________________________

LGA: _______________________________________________

Community/Town: _______________________________________________

Specific Location: _______________________________________________

(Example: Beside the market, Near the mosque, At XYZ Primary School)

## 1.3 WHO HAS THIS PROBLEM?

Describe the people affected:

Who are they? (Age, gender, occupation, etc.)

_______________________________________________

_______________________________________________

How many people approximately?

☐ 10-50 people

☐ 50-100 people

☐ 100-500 people

☐ 500-1000 people

☐ More than 1000 people

Why does it matter to them? (How does this problem affect their daily lives?)

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

## 1.4 WHEN DID THIS PROBLEM START?

Understanding the history helps you understand the cause.

When did this problem begin?

_______________________________________________

Is it getting worse, staying the same, or improving?

☐ Getting worse

☐ Staying the same

☐ Slightly improving (but still a problem)

Why?

_______________________________________________

_______________________________________________

## 1.5 WHY DOES THIS PROBLEM EXIST?

List at least 3 root causes:

Cause 1: _______________________________________________

Cause 2: _______________________________________________

Cause 3: _______________________________________________

Example:

Problem: Children drink dirty water

Root Causes:

1. No clean water source nearby

2. Community can't afford to build a borehole

3. Government promised but never delivered

## 1.6 HAS ANYONE TRIED TO SOLVE THIS BEFORE?

☐ Yes ☐ No ☐ Don't know

If YES, what did they try?

_______________________________________________

_______________________________________________

What happened? Why did it succeed or fail?

_______________________________________________

_______________________________________________

_______________________________________________

What can you learn from their experience?

_______________________________________________

_______________________________________________

## 1.7 GATHER EVIDENCE

Don't just assume. Collect real data.

I will gather evidence by: (Check all that apply)

☐ Interviewing community members (at least 10 people)

☐ Taking photos/videos of the problem

☐ Counting/measuring the problem (numbers)

☐ Asking community leaders

☐ Reviewing any existing data (school records, health reports, etc.)

☐ Personal observation over several days

List 5 people you will interview:

1. _______________________________________________

2. _______________________________________________

3. _______________________________________________

4. _______________________________________________

5. _______________________________________________

Key questions to ask them:

1. How does this problem affect you?

2. What do you think causes this problem?

3. What have you tried to do about it?

4. What would help solve this problem?

5. What resources do we have locally that could help?

## 1.8 PROBLEM STATEMENT (Final Version)

Now that you've researched, write a clear problem statement:

TEMPLATE:

"[Number] of [who] in [location] suffer from [problem] because [root cause]. This matters because [impact on their lives]."

YOUR PROBLEM STATEMENT:

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

Example:

"Over 500 primary school children in Mushin community lack access to books because our school has no library. This matters because children cannot practice reading at home, leading to poor literacy and exam failures."

# STEP 2: DESIGN YOUR SOLUTION

## WHY THIS MATTERS

Now that you understand the problem deeply, it's time to design your solution. A good solution:

Addresses the ROOT CAUSE, not just symptoms

Is realistic (you can actually do it)

Fits the local context (works for this specific community)

Uses available resources creatively

## 2.1 BRAINSTORM POSSIBLE SOLUTIONS

Don't judge ideas yet. Just brainstorm. List at least 5 different ways you could address this problem:

Possible Solution 1:

_______________________________________________

_______________________________________________

Possible Solution 2:

_______________________________________________

_______________________________________________

Possible Solution 3:

_______________________________________________

_______________________________________________

Possible Solution 4:

_______________________________________________

_______________________________________________

Possible Solution 5:

_______________________________________________

_______________________________________________

## 2.2 EVALUATE YOUR OPTIONS

For each solution above, rate it:

| Solution | Can we do it? (1-5) | Will it work? (1-5) | Is it sustainable? (1-5) | TOTAL |

|----------|---------------------|---------------------|--------------------------|-------|

| 1 | | | | |

| 2 | | | | |

| 3 | | | | |

| 4 | | | | |

| 5 | | | | |

(1 = Very unlikely, 5 = Very likely)

The solution with the highest total score is your best option.

## 2.3 CHOOSE YOUR SOLUTION

I will implement this solution:

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

Why did you choose this one?

_______________________________________________

_______________________________________________

_______________________________________________

## 2.4 HOW WILL YOUR SOLUTION WORK?

Describe in detail what you will actually DO:

Step-by-step description:

Step 1:

_______________________________________________

_______________________________________________

Step 2:

_______________________________________________

_______________________________________________

Step 3:

_______________________________________________

_______________________________________________

Step 4:

_______________________________________________

_______________________________________________

Step 5:

_______________________________________________

_______________________________________________

(Add more steps as needed)

## 2.5 WHY WILL THIS SOLUTION WORK?

Explain the logic behind your solution:

This solution will work because:

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

Evidence that supports this approach:

_______________________________________________

_______________________________________________

_______________________________________________

## 2.6 WHAT COULD GO WRONG?

Think ahead about potential problems:

Risk 1:

_______________________________________________

How I'll prevent/handle it:

_______________________________________________

_______________________________________________

Risk 2:

_______________________________________________

How I'll prevent/handle it:

_______________________________________________

_______________________________________________

Risk 3:

_______________________________________________

How I'll prevent/handle it:

_______________________________________________

_______________________________________________

## 2.7 HAVE OTHERS DONE SOMETHING SIMILAR?

Research similar projects:

Project/Organization: _______________________________________________

What they did: _______________________________________________

_______________________________________________

What I can learn from them:

_______________________________________________

_______________________________________________

How my approach will be different/better:

_______________________________________________

_______________________________________________

# STEP 3: CREATE YOUR ACTION PLAN

## WHY THIS MATTERS

Ideas don't become reality without action. This section breaks your project into manageable tasks with deadlines.

## 3.1 PROJECT TIMELINE

Project Start Date: _______________________________________________

Project End Date: _______________________________________________

Total Duration: _______________________________________________

(National Builders projects run May-October = 6 months)

## 3.2 MAJOR MILESTONES

Break your project into 4-6 major phases:

Milestone 1: _______________________________________________

Target Date: _______________________________________________

What must be complete: _______________________________________________

_______________________________________________

Milestone 2: _______________________________________________

Target Date: _______________________________________________

What must be complete: _______________________________________________

_______________________________________________

Milestone 3: _______________________________________________

Target Date: _______________________________________________

What must be complete: _______________________________________________

_______________________________________________

Milestone 4: _______________________________________________

Target Date: _______________________________________________

What must be complete: _______________________________________________

_______________________________________________

(Add more milestones as needed)

## 3.3 MONTHLY BREAKDOWN

MONTH 1 (May):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables (what you'll complete):

_______________________________________________

_______________________________________________

MONTH 2 (June):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables:

_______________________________________________

_______________________________________________

MONTH 3 (July):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables:

_______________________________________________

_______________________________________________

MONTH 4 (August):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables:

_______________________________________________

_______________________________________________

MONTH 5 (September):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables:

_______________________________________________

_______________________________________________

MONTH 6 (October):

Main Activities:

_______________________________________________

_______________________________________________

_______________________________________________

Who's Responsible:

_______________________________________________

Deliverables:

_______________________________________________

_______________________________________________

## 3.4 WEEKLY SCHEDULE

What day(s) each week will you work on your project?

☐ Monday

☐ Tuesday

☐ Wednesday

☐ Thursday

☐ Friday

☐ Saturday

☐ Sunday

What time?

_______________________________________________

For how long?

_______________________________________________

Where?

_______________________________________________

## 3.5 TEAM ROLES & RESPONSIBILITIES

If you're working with a team, clarify who does what:

Team Member 1: _______________________________________________

Role/Responsibilities:

_______________________________________________

_______________________________________________

Team Member 2: _______________________________________________

Role/Responsibilities:

_______________________________________________

_______________________________________________

Team Member 3: _______________________________________________

Role/Responsibilities:

_______________________________________________

_______________________________________________

Team Member 4: _______________________________________________

Role/Responsibilities:

_______________________________________________

_______________________________________________

Team Member 5: _______________________________________________

Role/Responsibilities:

_______________________________________________

_______________________________________________

How often will your team meet?

☐ Daily

☐ Weekly

☐ Bi-weekly

☐ Monthly

Meeting Day/Time: _______________________________________________

Meeting Location: _______________________________________________

# STEP 4: MAP YOUR RESOURCES

## WHY THIS MATTERS

National Builders projects require RESOURCEFULNESS, not big budgets. You'll be surprised how much you can accomplish with creativity and hustle.

## 4.1 MATERIALS NEEDED

List everything you need:

| Item | Quantity | Where to Get It | Estimated Cost |

|------|----------|-----------------|----------------|

| | | | |

| | | | |

| | | | |

| | | | |

| | | | |

| | | | |

| | | | |

| | | | |

| | | | |

TOTAL ESTIMATED COST: ₦_______________

## 4.2 HOW WILL YOU GET MATERIALS?

For each major item, identify how you'll obtain it:

☐ BUY (with what money?)

Source of funds:

_______________________________________________

_______________________________________________

☐ BORROW (from whom?)

_______________________________________________

_______________________________________________

☐ DONATIONS (who might donate?)

Potential donors to approach:

1. _______________________________________________

2. _______________________________________________

3. _______________________________________________

4. _______________________________________________

5. _______________________________________________

☐ MAKE/BUILD (from local materials)

What materials are available locally for free/cheap?

_______________________________________________

_______________________________________________

_______________________________________________

☐ IN-KIND CONTRIBUTIONS (people donate services instead of money)

What services might people volunteer?

_______________________________________________

_______________________________________________

_______________________________________________

## 4.3 PEOPLE WHO WILL HELP

Volunteers:

List people who will volunteer their time:

Name: _______________________________________________

Skills: _______________________________________________

How they'll help: _______________________________________________

Name: _______________________________________________

Skills: _______________________________________________

How they'll help: _______________________________________________

Name: _______________________________________________

Skills: _______________________________________________

How they'll help: _______________________________________________

Experts/Advisors:

Who has expertise you need?

Name: _______________________________________________

Expertise: _______________________________________________

When you'll consult them: _______________________________________________

Name: _______________________________________________

Expertise: _______________________________________________

When you'll consult them: _______________________________________________

## 4.4 SKILLS YOU NEED TO LEARN

Be honest: What skills do you lack that your project requires?

Skill 1: _______________________________________________

How I'll learn it:

_______________________________________________

_______________________________________________

Skill 2: _______________________________________________

How I'll learn it:

_______________________________________________

_______________________________________________

Skill 3: _______________________________________________

How I'll learn it:

_______________________________________________

_______________________________________________

## 4.5 PARTNERSHIPS

Could you partner with any organizations?

Potential Partner 1: _______________________________________________

What they could provide:

_______________________________________________

_______________________________________________

How you'll approach them:

_______________________________________________

_______________________________________________

Potential Partner 2: _______________________________________________

What they could provide:

_______________________________________________

_______________________________________________

How you'll approach them:

_______________________________________________

_______________________________________________

# STEP 5: PLAN FOR IMPACT MEASUREMENT

## WHY THIS MATTERS

You need to PROVE your project made a difference. Numbers and stories are your evidence.

## 5.1 WHAT WILL YOU MEASURE?

Choose 3-5 key metrics:

Metric 1: _______________________________________________

How you'll count it:

_______________________________________________

Target number:

_______________________________________________

Metric 2: _______________________________________________

How you'll count it:

_______________________________________________

Target number:

_______________________________________________

Metric 3: _______________________________________________

How you'll count it:

_______________________________________________

Target number:

_______________________________________________

Metric 4: _______________________________________________

How you'll count it:

_______________________________________________

Target number:

_______________________________________________

Metric 5: _______________________________________________

How you'll count it:

_______________________________________________

Target number:

_______________________________________________

Example:

Metric: Number of children reading improved

How to count: Pre-test and post-test reading scores

Target: 80% of children improve by at least one grade level

## 5.2 BEFORE & AFTER

BEFORE (Baseline):

What does the situation look like NOW before your project starts?

Take measurements/photos in May:

_______________________________________________

_______________________________________________

_______________________________________________

Photos to take:

☐ Current state of the problem

☐ The location/area

☐ People affected

AFTER (End-line):

What will you measure in October to show change?

_______________________________________________

_______________________________________________

_______________________________________________

Photos to take:

☐ The solution in action

☐ Changed conditions

☐ Beneficiaries using/benefiting

☐ Before/after comparison

## 5.3 COLLECTING STORIES

Numbers alone aren't enough. You need human stories.

I will collect testimonials from:

☐ At least 3 beneficiaries

☐ At least 1 community leader

☐ At least 1 parent/elder

☐ Team members (what we learned)

Questions to ask beneficiaries:

1. How did this project help you?

2. What has changed in your life because of this?

3. What would you tell other communities about this project?

## 5.4 DOCUMENTATION PLAN

I will document my project by: (Check all that apply)

☐ Taking photos every week (minimum 5 photos per month)

☐ Recording short videos (testimonials, project work)

☐ Keeping a project journal/log

☐ Collecting receipts and records

☐ Writing monthly summaries

☐ Creating a project scrapbook

Who is responsible for documentation?

_______________________________________________

# STEP 6: BUILD SUSTAINABILITY

## WHY THIS MATTERS

Many projects die after the competition ends. National Builders create LASTING change.

## 6.1 WHAT HAPPENS AFTER OCTOBER?

Will your project continue after the National Builders challenge ends?

☐ Yes - here's how

☐ No - it's a one-time intervention

☐ Partially - some parts will continue

If YES, explain your sustainability plan:

_______________________________________________

_______________________________________________

_______________________________________________

_______________________________________________

## 6.2 WHO WILL MAINTAIN IT?

After you move on, who will keep this going?

_______________________________________________

_______________________________________________

What do they need to maintain it?

_______________________________________________

_______________________________________________

How will you train/prepare them?

_______________________________________________

_______________________________________________

## 6.3 ONGOING RESOURCES

What ongoing resources does this project need?

_______________________________________________

_______________________________________________

Where will those resources come from?

_______________________________________________

_______________________________________________

## 6.4 SCALING POTENTIAL

Could this project be replicated in other communities?

☐ Yes

☐ No

☐ Maybe

If YES, what would other communities need to copy your model?

_______________________________________________

_______________________________________________

_______________________________________________

What advice would you give them?

_______________________________________________

_______________________________________________

_______________________________________________

# SAMPLE PROJECT EXAMPLES

## EXAMPLE 1: COMMUNITY LIBRARY PROJECT

Problem: Primary school has 500 students but no library. Children can't practice reading.

Solution: Create a simple community library using donated books and local volunteers.

Action Plan:

May: Collect 200 books through donation drive

June: Build simple bookshelves from recycled materials

July: Train 5 volunteer librarians from the community

August-September: Open library 3 days per week, track usage

October: Measure reading improvement in students

Resources:

Donated books from churches, NGOs, individual homes

Recycled wood for shelves (from local carpenter)

Volunteer time from parents and retired teachers

Classroom space donated by school

Impact Measurement:

Number of books collected

Number of children using library weekly

Reading test scores (before/after)

Parent testimonials

Sustainability:

Parent-Teacher Association will manage library

Monthly book donations from community

Volunteer rotation schedule created

Estimated Cost: ₦15,000 (for paint, nails, labels, registration system)

## EXAMPLE 2: WASTE RECYCLING INITIATIVE

Problem: Market area has no waste management. Garbage piles up, causing health problems and flooding.

Solution: Organize weekly cleanup + recycling system where plastic bottles are collected and sold.

Action Plan:

May: Map waste hotspots, meet with market leaders

June: Recruit 10 youth volunteers, get recycling company contact

July-August: Weekly cleanups every Saturday morning

September: Create permanent waste collection points

October: Measure waste reduced, income generated from selling recyclables

Resources:

Volunteer youth labor (no cost)

Donated gloves and bags from local businesses

Partnership with recycling company (buys plastic)

Market association provides storage space

Impact Measurement:

Tons of waste collected each month

Number of volunteers participating

Money earned from recycling

Flood incidents reduced (compare to last year)

Before/after photos of market cleanliness

Sustainability:

Money from selling recyclables funds ongoing operations

Youth volunteers rotate, train new people

Market association incorporates into regular maintenance

Estimated Cost: ₦8,000 (initial supplies, transportation for first month)

## EXAMPLE 3: YOUTH SKILLS TRAINING

Problem: Many youth ages 16-25 in community are unemployed with no marketable skills.

Solution: Weekly vocational training in tailoring, phone repair, and hairdressing using local experts.

Action Plan:

May: Survey youth needs, recruit 3 skilled trainers from community

June: Enroll 30 youth, begin Saturday training sessions

July-September: Weekly 2-hour sessions, each person learns one skill

October: Graduation ceremony, help youth start micro-businesses

Resources:

Volunteer trainers (experienced tailors, phone technicians, hairdressers)

Community center space (free)

Used sewing machines (borrowed/donated)

Startup kits (small tools) donated by local businesses

Impact Measurement:

Number of youth trained

Number who start earning income

Testimonials about life change

Skills tests before/after training

Sustainability:

Graduated students become trainers for next cohort

Students pay small fee (₦500) if they can afford, creating fund for materials

Partner businesses hire graduates

Estimated Cost: ₦25,000 (materials, certificates, startup kits for 5 top performers)

# COMMON MISTAKES TO AVOID

## MISTAKE 1: Planning alone without community input

Why it's bad: Your solution might not match what people actually need.

How to avoid: Interview at least 10 community members before finalizing your plan.

## MISTAKE 2: Over-ambitious plans you can't finish

Why it's bad: Better to do one thing excellently than five things poorly.

How to avoid: Be realistic. Can you actually do this in 6 months with your resources?

## MISTAKE 3: No backup plan for when things go wrong

Why it's bad: Things WILL go wrong. If you haven't thought ahead, you'll panic and quit.

How to avoid: For every major risk, have a "Plan B" ready.

## MISTAKE 4: Forgetting to document as you go

Why it's bad: In October, you'll struggle to remember what you did. You'll have no proof.

How to avoid: Take photos EVERY time you work. Keep a simple journal.

## MISTAKE 5: Depending on one person for everything

Why it's bad: If that person gets sick or quits, your whole project collapses.

How to avoid: Distribute responsibilities. Train backups.

## MISTAKE 6: Ignoring advice from elders/experts

Why it's bad: They have experience you lack. Their wisdom could save you months of mistakes.

How to avoid: Regularly consult your advisor. Listen with humility.

## MISTAKE 7: No plan for what happens after October

Why it's bad: Your project dies the moment the competition ends. No lasting impact.

How to avoid: Build sustainability into your plan from Day 1.

# FINAL PLANNING CHECKLIST

Before you start implementing, check that you've completed:

PROBLEM UNDERSTANDING:

☐ I clearly understand the problem I'm solving

☐ I know the root causes, not just symptoms

☐ I've interviewed at least 10 people affected by this problem

☐ I have evidence (photos, numbers) showing the problem exists

☐ I've written a clear problem statement

SOLUTION DESIGN:

☐ I've brainstormed multiple possible solutions

☐ I've evaluated which solution is most feasible

☐ I can explain step-by-step how my solution will work

☐ I've researched what others have done

☐ I've identified potential risks and have backup plans

ACTION PLAN:

☐ I have a detailed timeline with monthly milestones

☐ I know exactly what I'll do each month

☐ I've assigned responsibilities to team members

☐ I have a regular schedule for working on the project

☐ I have realistic deadlines

RESOURCES:

☐ I've listed all materials I need

☐ I know where I'll get each material (buy/borrow/donate/make)

☐ I've identified all volunteers and their roles

☐ I've identified skills I need to learn and how I'll learn them

☐ I have a realistic budget

IMPACT MEASUREMENT:

☐ I know exactly what I'll measure (3-5 metrics)

☐ I'll take "before" measurements/photos in May

☐ I'll take "after" measurements/photos in October

☐ I have a plan to collect testimonials

☐ I'll document my project with photos/videos regularly

SUSTAINABILITY:

☐ I have a plan for what happens after October

☐ I know who will maintain/continue the project

☐ I've identified ongoing resource needs

☐ I've thought about how this could be replicated elsewhere

VALUES INTEGRATION:

☐ I've identified which 3 values will guide my project

☐ I can explain how each value applies to my work

☐ I've signed my Values Commitment in Workbook 1

IF YOU CHECKED ALL BOXES ABOVE, YOU'RE READY TO START!

IF YOU CHECKED FEWER THAN 80%, GO BACK AND COMPLETE THE MISSING SECTIONS.

# YOU'RE READY TO BUILD!

Congratulations! You now have a solid project plan.

Remember:

Your plan is a LIVING DOCUMENT - update it as you learn

Review this plan at the start of each month

Share it with your mentor for feedback

Don't be afraid to adjust when needed

But most importantly: START.

Planning is important, but ACTION is what creates impact.

Your community is waiting for you, National Builder.

Now go make it happen! 🇳🇬

# END OF PROJECT PLANNING GUIDE

For more resources and support, visit:

📱 Website: KidsInspiringNation.org

💬 WhatsApp: [Coordinator Number]

📧 Email: KidsInspiringNation@gmail.com

Next Steps:

1. Complete this planning guide thoroughly

2. Review with your mentor

3. Revise based on feedback

4. START IMPLEMENTING in May!

© 2025 National Builders Corp. All Rights Reserved.

Permission granted to photocopy for personal use by registered NBC participants.